## Cover
PLF-KS REGRESSION TEST CASES
Version:	1.2
Issue date:	29-Feb-2012
Project Suite:
Project Name:	KS
Total Cases:	11
Test Status:	Passed: Test is OK / Blocked: Could not run the test (another bug is blocking) / Failed: Test failed, a bug is entered on it (please add the bug ID) / N/A: Test is not possible to run on this version

Record of change:
Effective Date	Version	Change description	Originator	Reviewer/ / Approver	Reference
6-Oct-2011	1.0	Write Regression test for KS	Hang.Nguyen
17-Jan-2012	1.1	Review and update testcase	Nhung.Vu
29-Feb-2012	1.2	Add content for Bugs_v2_1_8 sheet	Hanh.Ly
24-May-2012	1.3	Add content for Bugs_v2_1_9 sheet	Thao.Pham
24-Jul-2012	1.3	Update comment TC 3.5.4, Bug_v2_1_5 - case No 01, Bug_v2_1_9- case No 01	Thu.Nguyen
24-May-2012	1.3	Modify case 02 for Bugs_v2_1_5 sheet	Thu.Nguyen

## Check_List
Check List / Based on Product built version: KS 2.1.x
Id	Main cases	Priority	Selenium
Bugs v.2.1.4
REG_PLF_214_KS_001	Check The Maximum number of on line users	Medium
REG_PLF_214_KS_002	Check French translation in Faq Answer portlet	Medium
Bugs v.2.1.5
REG_PLF_215_KS_001	Check An inactive and/or disapproved question is always visible in FAQ	High
REG_PLF_215_KS_002	Forum "Private Message" posts are visible in the global activity stream	High
REG_PLF_215_KS_003	Check FN/LN display in vote	High
REG_PLF_215_KS_004	Polls are visible for all users	High
Bugs v.2.1.6
REG_PLF_216_KS_001	Check Popup Resize in Settings form	Medium
Bugs v.2.1.8
REG_PLF_218_KS_001	Re-order category	High
REG_PLF_218_KS_002	Check the appearance of question when category is moderated	High
REG_PLF_218_KS_003	Check disactivated question in Manage Question form	Medium
REG_PLF_218_KS_004	Check manager of forum in space	Medium

## Bugs_v2_1_4
	TEST CASES					Passed	6	6	0	0	0	0	0
				Failed	0	0	0	0	0	0	0
	Function List:	Bugs on KS 2.1.6 for regression test					Blocked	0	0	0	0	0	0	0
	Total Main Cases:	2					Untested	0	0	0	0	0	0	0
				N/A	0	0	0	0	0	0	0
Case No	Related function	Case ID	Path	Case Description	Step Description	Steps to produce	Expected Output	Priority	Link	Bug description	Tester	IE7	FireFox3.5	Comment/Bug
001	REG_PLF_214_KS_001	001	REG_PLF_214_KS_001	Check The Maximum number of online users	Step 1: Login with some user	- Login as "john", "mary" and "demo" on three respective browsers.	Login in successfully	Medium	KS-3065 / CCP_786	The max user in forum is not set properly	thu.nguyen	Passed	Passed
	REG_PLF_214_KS_001	001	REG_PLF_214_KS_001	Check The Maximum number of online users	Step 2: Check the maximum numbers of on line users	- With each users go to Forum	Show the maximum number of online user	Medium			thu.nguyen	Passed	Passed
	REG_PLF_214_KS_001	001	REG_PLF_214_KS_001	Check The Maximum number of online users	Step 3: Check after logout user	- Logout mary	The Number of maximum users will be updated after 2m	Medium			thu.nguyen	Passed	Passed
002	REG_PLF_214_KS_002	001	REG_PLF_214_KS_002	Check French translation in Answer portlet	Step 1: Add new page with Answer portlet	Step 1: Add new page have FAQ answer portlet	Add new page successfully	Medium	KS-3075 / CCP_796	Problem with French translation in Faq Answer portlet	thu.nguyen	Passed	Passed
	REG_PLF_214_KS_002	001	REG_PLF_214_KS_002	Check French translation in Answer portlet	Step 2: Check Answer button	- Change language to French / - Add new question with French language / - Click on new question and click Answer button	We have "Answers" should be "Réponse"	Medium			thu.nguyen	Passed	Passed
	REG_PLF_214_KS_002	001	REG_PLF_214_KS_002	Check French translation in Answer portlet	Step 3: Check datetime label of question	- Check datetime label / + “Just Now” / + "1 minute ago" / + “1 hour ago”	They should be: / + “Maintenant” / + "Il y a 1 minute" / + "Il y a 1 heure"	Medium			thu.nguyen	Passed	Passed

## Bugs_v2_1_5
	TEST CASES					Passed	18	18	0	0	0	0	0
				Failed	0	0	0	0	0	0	0
	Function List:	Bugs on KS 2.1.6 for regression test					Blocked	0	0	0	0	0	0	0
	Total Main Cases:	4					Untested	0	0	0	0	0	0	0
				N/A	0	0	0	0	0	0	0
Case No	Related function	Case ID	Path	Case Description	Step Description	Steps to produce	Expected Output	Priority	Link	Bug description	Tester	IE7	FireFox3.5	Comment/Bug
001	REG_PLF_215_KS_001	001	REG_PLF_215_KS_001	Check An inactive and/or disapproved question is always visible in FAQ	Step 1: Add new for Answer and FAQ page	- Login by root / - Add new page with Answer portlet and FAQ portlet	Add new page successfully	High	KS-3035 / CCP_638	An inactived and/or disapproved question is always visible in FAQ	thu.nguyen	Passed	Passed
	REG_PLF_215_KS_001	001	REG_PLF_215_KS_001	Check An inactive and/or disapproved question is always visible in FAQ	Step 2: Add new some questions and answer	- Click Submit question / - Add some question / - Click Answer to add some answer for some question	Question and answer is created successfully	High			thu.nguyen	Passed	Passed
	REG_PLF_215_KS_001	001	REG_PLF_215_KS_001	Check An inactive and/or disapproved question is always visible in FAQ	Step 3: Check manage question	- Go to Manage question on AnswerToolbar	This question and answer are activated and approved by default	High			thu.nguyen	Passed	Passed
	REG_PLF_215_KS_001	001	REG_PLF_215_KS_001	Check An inactive and/or disapproved question is always visible in FAQ	Step 4: Check all answer and question in FAQ	- Go to FAQ page	They're visibles in Answers/FAQ page.	High			thu.nguyen	Passed	Passed
	REG_PLF_215_KS_001	001	REG_PLF_215_KS_001	Check An inactive and/or disapproved question is always visible in FAQ	Step 5: Uncheck both Approved and Activated	- Go to Manage question on AnswerToolbar / - uncheck both Approved and Activated. Then Save	Uncheck both Approved and Activated sucessfully	High			thu.nguyen	Passed	Passed
	REG_PLF_215_KS_001	001	REG_PLF_215_KS_001	Check An inactive and/or disapproved question is always visible in FAQ	Step 6: Check question after unchecked Approved and Activated in Answer page	- Go to Answer page	This question is no more visible in module "Answers"	High			thu.nguyen	Passed	Passed
	REG_PLF_215_KS_001	001	REG_PLF_215_KS_001	Check An inactive and/or disapproved question is always visible in FAQ	Step 7: Check answer and question in FAQ	- Go to FAQ page	This question is invisible in FAQ	High			thu.nguyen	Passed	Passed
002	REG_PLF_215_KS_002	002	REG_PLF_215_KS_002	Forum "Private Message" posts are visible in the global activity stream	Step 1: Send private message to demo and john	- Login by root / - Choose My space and click Add new space / - Input some fields required with name is Space1 / - Click Save	Private message's sent to demo and john successfully	High	KS-3160 / CCP_855		thu.nguyen	Passed	Passed
	REG_PLF_215_KS_002	002	REG_PLF_215_KS_002	Forum "Private Message" posts are visible in the global activity stream	Step 2: Invite john and demo to this space.	- Click on Space1 and choose space setting icon on Space Menu Portlet / - Choose member tab and invite demo, john join Space1	Invitations to demo and john successfully	High			thu.nguyen	Passed	Passed
	REG_PLF_215_KS_002	002	REG_PLF_215_KS_002	Forum "Private Message" posts are visible in the global activity stream	Step 3: Send a private message to john.	- Go to Forum / - Click Private message send private message to John	Send new message successfully	High			thu.nguyen	Passed	Passed
	REG_PLF_215_KS_002	002		Forum "Private Message" posts are visible in the global activity stream	Step 4: Connect to demo	- Go to Find connection / - Click on Connect to demo	Connection request is sent to demo	High
	REG_PLF_215_KS_002	002	REG_PLF_215_KS_002	Forum "Private Message" posts are visible in the global activity stream	Step 5: Confirm the connection request	- Login as demo / - Go to My connection / - Click on Request received / - Click on Confirm	Demo is connected to root	High			thu.nguyen	Passed	Passed
	REG_PLF_215_KS_002	002	REG_PLF_215_KS_002	Forum "Private Message" posts are visible in the global activity stream	Step 6: Check private message in Demo's activity	- Go to intranet homepage / - Check All Updates	Private message cannot be displayed in his activity stream	High
003	REG_PLF_215_KS_003	003	REG_PLF_215_KS_003	Check FN/LN display in vote	Step 1: Created Category/Forum/Topic	- Go to Forum / - Created Category/Forum/Topic	Created Category/Forum/Topic successfully	High	KS-3214 / CCP_888	First/last name should be displayed in vote rather than user name	thu.nguyen	Passed	Passed
	REG_PLF_215_KS_003	003	REG_PLF_215_KS_003	Check FN/LN display in vote	Step 2: Vote rate for topic	Open the Topic and click Rate	- Rate for topic successfully / - Rating info is shown correct in Forum	High			thu.nguyen	Passed	Passed
	REG_PLF_215_KS_003	003	REG_PLF_215_KS_003	Check FN/LN display in vote	Step 3: Vote again for topic	Continue click rate for topic again	Private message's sent to demo and john successfully	High			thu.nguyen	Passed	Passed
004	REG_PLF_215_KS_004	004	REG_PLF_215_KS_004	Polls are visible for all users	Step 1: Create new space	- Login by John / - Create new space with name Space1	- Space1 is created successfully / - On Forum page, a forum named Space1 is created under Category spaces	High	KS-3224 / CCP_896	Polls are visible for all users	thu.nguyen	Passed	Passed
	REG_PLF_215_KS_004	004	REG_PLF_215_KS_004	Polls are visible for all users	Step 2: Add new forum under the space	- Click on Dicussion on Space1	Forum Space1 is opened	High			thu.nguyen	Passed	Passed
	REG_PLF_215_KS_004	004	REG_PLF_215_KS_004	Polls are visible for all users	Step 3: Create new topic and add a poll to this topic	- Create Topic1 / - Open topic and click Add poll on More Action / - Input some field required and click Submit Poll	- Topic1 is created successfully / - Add new poll successfully	High			thu.nguyen	Passed	Passed
	REG_PLF_215_KS_004	001	REG_PLF_215_KS_004	Polls are visible for all users	Step 4: Login by mary to check all the poll questions of all topics when adding the Poll Gadget	- Login by mary, she is not a member of Space1 / - Click Dashboard / - Click Add gadget and drag & drop Feature Poll	She can't see all the poll questions of all topics when adding the Poll Gadget	High			thu.nguyen	Passed	Passed

## Bugs_v2_1_6
	TEST CASES					Passed	1	1	0	0	0	0	0
				Failed	0	0	0	0	0	0	0
	Function List:	Bugs on KS 2.1.6 for regression test					Blocked	0	0	0	0	0	0	0
	Total Main Cases:	1					Untested	0	0	0	0	0	0	0
				N/A	0	0	0	0	0	0	0
Case No	Related function	Case ID	Path	Case Description	Step Description	Steps to produce	Expected Output	Priority	Link	Bug description	Tester	IE7	FireFox3.5	Comment/Bug
001	REG_PLF_216_KS_001	001	REG_PLF_216_KS_001	Check Popup Resize in Settings form	Step 1: Check resize pop-up	- Go to Forum / - Click Settings icon on Forum Action Bar / - Resize pop-up	All the text on page aren't selected	Medium	KS-3407 / CCP_835	Pop-up resize problem	thu.nguyen	Passed	Passed

## Bugs_v2_1_8
	TEST CASES					Passed	20	20	0	0
				Failed	0	0	0	0
	Function List:	Bugs on KS 2.1.8 for regression test					Blocked	0	0	0	0
	Total Main Cases:	4					Untested	0	0	0	0
				N/A	0	0	0	0
Case No	Related function	Case ID	Path	Case Description	Step Description	Steps to produce	Expected Output	Priority	Link	Bug description	Tester	IE7	FireFox3.5	Comment/Bug
001	REG_PLF_218_KS_001	001	REG_PLF_218_KS_001	Re-order category	Step 1: Create categories	- Login by admin / - Go to Answer page / - Create 3 categories named AAA, BBB, CCC in order	- 3 categories are created successfully. / - The order of category AAA is 1 / - The order of category BBB is 2 / - The order of category CCC is 3	High	KS-4032 / CCP-1062	The order is not changed	thu.nguyen	Passed	Passed
	REG_PLF_218_KS_001	001	REG_PLF_218_KS_001	Re-order category	Step 2: Re-order category	- Right click on category CCC and select Edit / - Change the order of category is 10 / - Click Save button	- Category CCC still in the third place / - In the edit form, value in order field is 3	High			thu.nguyen	Passed	Passed
	REG_PLF_218_KS_001	001	REG_PLF_218_KS_001	Re-order category	Step 3: Re-order category	- Right click on category CCC and select Edit / - Change the order of category is 1 / - Click Save button	- Category CCC is in the first place / - In the edit form, value in order field is 1	High			thu.nguyen	Passed	Passed
	REG_PLF_218_KS_001	001	REG_PLF_218_KS_001	Re-order category	Step 4: Re-order category	- Right click on category CCC and select Edit / - Change the order of category is 2 / - Click Save button	- Category CCC is in the second place / - In the edit form, value in order field is 2	High			thu.nguyen	Passed	Passed
002	REG_PLF_218_KS_002	001	REG_PLF_218_KS_002	Check the appearance of question when category is moderated	Step 1: Create category with moderate new questions	- Login with John / - Go to Answer page / - Open form to add new category: / - Fill the Category's name / - Check on Moderate new questions / - Save	New category is created successfully	High	KS-4051 / CCP-1187	Question is available	thu.nguyen	Passed	Passed
	REG_PLF_218_KS_002	001	REG_PLF_218_KS_002	Check the appearance of question when category is moderated	Step 2: Create question by normal user	- Login as mary / - Go to Answer page / - Select category above / - Submit a new question "John is good?"	The created question in status waiting the category's moderator to approve.	High			thu.nguyen	Passed	Passed
	REG_PLF_218_KS_002	001	REG_PLF_218_KS_002	Check the appearance of question when category is moderated	Step 3: Approve question	- Login as john / - Click on Manage Questions / - Approve question created by mary above	Question is approved. It's visible for every user	High			thu.nguyen	Passed	Passed
	REG_PLF_218_KS_002	001	REG_PLF_218_KS_002	Check the appearance of question when category is moderated	Step 4: Edit question	- Login as mary / - Right click on created question and select Edit / - Change content of question / - Save	The created question in status waiting the category's moderator to approve.	High			thu.nguyen	Passed	Passed
	REG_PLF_218_KS_002	001	REG_PLF_218_KS_002	Check the appearance of question when category is moderated	Step 5: Check the appearance of question by admin	- Login as john	The created question in status waiting the category's moderator to approve.	High			thu.nguyen	Passed	Passed
	REG_PLF_218_KS_002	001	REG_PLF_218_KS_002	Check the appearance of question when category is moderated	Step 6: Check the appearance of question by other users	- Login by demo / - Go to Answer page / - Select category at step 1	The question created by mary is not appeared	High			thu.nguyen	Passed	Passed
003	REG_PLF_218_KS_003	001	REG_PLF_218_KS_003	Check disactivated question in Manage Question form	Step 1: Create a new space	- Login by demo / - Go to intranet site / - Go to Find Spaces / - Click on Add new space button / - Put space's name / - Click Create	New space is created successfully	Medium	KS-3428 / CCP-997	Disactivated question is not listed in Manage Question form	thu.nguyen	Passed	Passed
	REG_PLF_218_KS_003	001	REG_PLF_218_KS_003	Check disactivated question in Manage Question form	Step 2: Create question in space	- Select created space above / - Go to Answer application of space / - Click on Submit Question / - Put question's title and question's content / - Click Save	New question is created successfully	Medium			thu.nguyen	Passed	Passed
	REG_PLF_218_KS_003	001	REG_PLF_218_KS_003	Check disactivated question in Manage Question form	Step 3: Disactivated question	- Right click on question and select Edit / - Uncheck on Activated check-box / - Save	The question disappeared	Medium			thu.nguyen	Passed	Passed
	REG_PLF_218_KS_003	001	REG_PLF_218_KS_003	Check disactivated question in Manage Question form	Step 4: Check disactivated question in Manage Question form	- Click on Manage Questions	Disactivated question is listed in Manage Question form	Medium			thu.nguyen	Passed	Passed
004	REG_PLF_218_KS_004	001	REG_PLF_218_KS_004	Check manager of forum in space	Step 1: Create 2 users	- Login by root / - Create 2 users: user1 and user2	2 users are created successfully	Medium	KS-3815 / CCP-1131	Both user1 and user2 are moderator of space	thu.nguyen	Passed	Passed
	REG_PLF_218_KS_004	001	REG_PLF_218_KS_004	Check manager of forum in space	Step 2: Create new space by user1	- Login by user1 / - Go to Find Spaces / - Click on Add new space button / - Put space's name: test1space / - Save	New space is created successfully	Medium			thu.nguyen	Passed	Passed
	REG_PLF_218_KS_004	001	REG_PLF_218_KS_004	Check manager of forum in space	Step 3: Create new space by user2	- Login by user2 / - Go to Find Spaces / - Click on Add new space button / - Put space's name: test2space / - Save	New space is created successfully	Medium			thu.nguyen	Passed	Passed
	REG_PLF_218_KS_004	001	REG_PLF_218_KS_004	Check manager of forum in space	Step 4: User2 join test1space	- Still login with user2 / - Go to public space / - Request to join test1space created by user1	A request is sent to user1	Medium			thu.nguyen	Passed	Passed
	REG_PLF_218_KS_004	001	REG_PLF_218_KS_004	Check manager of forum in space	Step 5: Accept request	- Login by user1 / - Go to test1space / - Go to Space Setting → Member / - Accept the request to join space of user2	User2 become a member of test1space	Medium			thu.nguyen	Passed	Passed
	REG_PLF_218_KS_004	001	REG_PLF_218_KS_004	Check manager of forum in space	Step 6: Check the manager of forum in space	- Still login with user1 / - Go to Forum application in space	The moderator of test1space is only user1	Medium			thu.nguyen	Passed	Passed

## Bugs_v2_1_9
	TEST CASES					Passed	8	8	0	0	0	0	0
				Failed	0	0	0	0	0	0	0
	Function List:	Bugs on KS 2.1.6 for regression test					Blocked	0	0	0	0	0	0	0
	Total Main Cases:	1					Untested	0	0	0	0	0	0	0
				N/A	0	0	0	0	0	0	0
Case No	Related function	Case ID	Path	Case Description	Step Description	Steps to produce	Expected Output	Priority	Link	Bug description	Tester	IE7	FireFox3.5	Comment/Bug
001	REG_PLF_219_KS_001	001	REG_PLF_219_KS_001	Check related questions list on answer portlet of space	Step 1: Create space by John	- Login as John, go to Intranet home / - Go to My spaces page and add new space	- New space is added	High	KS-4327 / CCP-1284	All questions is displayed in related question when submit an answer even user is not member of its space	thu.nguyen	Passed	Passed
	REG_PLF_219_KS_001	001	REG_PLF_219_KS_001	Check related questions list on answer portlet of space	Step 2: Invite Mary to become member	- Access space, go to settings portlet / - Select Member tab, invites Mary to join space	- Invitation is sent to Mary	High			thu.nguyen	Passed	Passed
	REG_PLF_219_KS_001	001	REG_PLF_219_KS_001	Check related questions list on answer portlet of space	Step 3: Mary accepts the invitation	- Login as Mary, go to My spaces page / - Select Invitation Received tab and accept the invitation from space above	- Mary becomes member of space	High			thu.nguyen	Passed	Passed
	REG_PLF_219_KS_001	001	REG_PLF_219_KS_001	Check related questions list on answer portlet of space	Step 4: Create space by Root	- Login as Root, go to Intranet home / - Go to My spaces page and add new space	- New space is added	High			thu.nguyen	Passed	Passed
	REG_PLF_219_KS_001	001	REG_PLF_219_KS_001	Check related questions list on answer portlet of space	Step 5: Invites James to become member	- Access space, go to settings portlet / - Select Member tab, invites James to join space	- Invitation is sent to James	High			thu.nguyen	Passed	Passed
	REG_PLF_219_KS_001	001	REG_PLF_219_KS_001	Check related questions list on answer portlet of space	Step 6: James accepts the invitation	- Login as James, go to My spaces page / - Select Invitation Received tab and accept the invitation from space above	- James becomes member of space	High			thu.nguyen	Passed	Passed
	REG_PLF_219_KS_001	001	REG_PLF_219_KS_001	Check related questions list on answer portlet of space	Step 7: Submit question on answer portlet of space	- Access space created by John, go to Answer portlet and submit a question / - Access space created by Root, go to Answer portlet and submit a question	- Question is submitted successfully / - Display only space which user is member,	High			thu.nguyen	Passed	Passed
	REG_PLF_219_KS_001	001	REG_PLF_219_KS_001	Check related questions list on answer portlet of space	Step 8: Add answer for any question	- Login as John, go to her space, select a question and add answer / - Click on “Related to” button	- Display form Related questions to select, display only question in space which John is member, do not display question in space created by Root (because John is not member of this space)	High			thu.nguyen	Passed	Passed

## Summary_Report
KS Regression Tests List					Total cases

Id	Product	Functionality	Bug summary	Product bugID
Bugs v.2.1.4
REG_PLF_214_KS_001	KS		Check The Maximum number of on line users	KS-3065 / CCP_786	1
REG_PLF_214_KS_002	KS		Check French translation in Faq Answer portlet	KS-3075 / CCP_796	1
Bugs v.2.1.5
REG_PLF_215_KS_001	KS		Check An inactive and/or disapproved question is always visible in FAQ	KS-3035 / CCP_638	1
REG_PLF_215_KS_002	KS		Forum "Private Message" posts are visible in the global activity stream	KS-3160 / CCP_855	1
REG_PLF_215_KS_003	KS		Check FN/LN display in vote	KS-3214 / CCP_888	1
REG_PLF_215_KS_004	KS		Polls are visible for all users	KS-3224 / CCP_896	1
Bugs v.2.1.6
REG_PLF_216_KS_001	KS		Check Popup Resize in Settings form	KS-3407 / CCP_835	1
Bugs v.2.1.6					0
REG_PLF_218_KS_001	KS		Re-order category		1
REG_PLF_218_KS_002	KS		Check the appearance of question when category is moderated		1
REG_PLF_218_KS_003	KS		Check disactivated question in Manage Question form		1
REG_PLF_218_KS_004	KS		Check manager of forum in space		1

Total					11